## Sheet1
| Time | January |  |  |  | February |  |  |  | March |  |  |  | April
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Development
Research | Explore options | bar: January Week 1 to January Week 2
Obtain academic approval | bar: January Week 2
Compile information | bar: January Week 2 to February Week 7
Content | Write text | bar: January Week 2 to February Week 7
Locate & acquire audio | bar: January Week 2 to January Week 3
Digitise audio | bar: January Week 3
Locate & acquire images | bar: January Week 4 to February Week 5
Digitise images | bar: February Week 5
Locare & acquire video | bar: February Week 6 to February Week 7
Digitise video | bar: February Week 7
HTML | Create templates | bar: February Week 5 to February Week 7
Add content | bar: February Week 6 to February Week 7
CSS | Create templates | bar: February Week 6 to February Week 8
Add styles | bar: February Week 7 to February Week 8
Javascript | Create templates | bar: February Week 8 to March Week 10
Add functions | bar: March Week 9 to March Week 10
Testing | bar: March Week 9 to March Week 12
Evaluation | bar: March Week 11 to March Week 12
Deadline